## Consolidated Roadmap Draft
Vanuatu Draft Climate Finance Roadmap 2016-2020 Based on the recommendations of the 2014 CPEIR, the 2016 Climate Finance Forum, the CCDRR Policy, the PFEM Roadmap, and 2017 Consultations | [5 empty] | Roadmap Focal Point: | Wycliff Bakeo |  |  | NAB CFWG & Prime Minister's Offcie (DSPPAC)
[6 empty] | Version Control 13.10.17 |  |  |  | wbakeo@vanuatu.gov.vu
Comments DFAT/GIZ HS from 31.03.17, SPC/ISACC - 18.4.17
Climate Finance Policy Objectives | Targets | Indicators | Ref number | Activities | Status of Activities | Sub-Activities | Timelines | [9 empty] | Partnerships |  |  |  | Policy Alignments | CFWG assigned importance 0 - 5 | CFWG assigned urgency 0 - 5 | Notes
[7 empty] | Q4, 2016 | Q1, 2017 | Q2, 2017 | Q3, 2017 | Q4, 2017 | 2018 | 2019 | 2020 | 2025 | 2030 | Govt | NGOs & CSOs | Private Sector | Development Partners
1. Access to Climate Change Finance: Vanuatu has access to direct and indirect new sources of climate and disaster finances to adapt to and mitigate the impacts of climate change. | The Government of Vanuatu's access to climate finance is increased - adaptation share of climate finance investment is at least 50%. |  | 1.1 | NAB establishes the Climate Finance Working Group to develop, monitor and report against the National Climate Finance Roadmap | [12 empty] | CFWG, PMO, NAB | VCAN | VCCI | GIZ, UNDP, ISACC |  | 2 | 2
|  |  | 1.1.1 |  |  | NAB develops and endorses CFWG Terms of Reference and multi-year action plan | [10 empty] | NAB Sec |  |  | GIZ
|  |  | 1.2 | Develop and endorse a National Climate Finance Roadmap | [12 empty] | CFWG |  |  | SPC/GIZ, DFAT/GIZ, GIZ Readiness, ISAAC, UNDP |  | 2 | 5 | Govt. needs to nominate focal point for Climate Finance Roadmap; Development Partners can support the focal point when and if requested. Development partners fit specific developments into this Roadmap through the focal point.
|  |  | 1.2.1 |  |  | Identify key national priorities through a Climate Finance Forum | [10 empty] | PMO, DSPPAC |  |  | DFAT / GIZ, ISACC |  | 2 | 3
|  |  | 1.3 | Work towards implementing the CCDRR policy to have equal share of adaptation and mitigation CF projects
|  |  | 1.3.1 |  |  | Design, approve and implement bankable, multi-sector projects and program proposals | [11 empty] | Save the Children (proposal in pipeline) |  | Climate Ready, DFAT / GIZ, ISACC, GIZ Readiness, ADB (proposal in pipeline) |  | 1 | 0 | See extensive sub-activities under private sector engagement on this activity. Note that NAB keeps a rolling database of GCF concept notes. Worth having a public facing, collaborative copy of this database? See Activity 5.2. CARE & Save the Children have expressed interest in collaborating on this activity. GIZ/DFAT starts this activity rather in the Q4 of 2017, unless opportunities arise earlier. CR will also consider this activity in Q4 of 2017
|  |  | 1.4 | Strengthen & expand innovative modalities | [12 empty] | CFWG, NAB | [7 empty] | entry 13.10.17
[6 empty] | Establish & operationalize the NGEF | [10 empty] | NGEF Taskforce |  |  | GGGI
| - At least one national entity is accredited as an NIE to the GCF/AF by 2020 - At least 80% of CPEIR recommendations are implemented by December 2017. |  | 1.5 | Seek GCF/AF NIE Accreditation | [12 empty] | MoCC |  |  |  |  | 5 | 3
|  |  | 1.5.1 |  |  | Roll out self assessment tool to selected NGOs, PS and government entities | [10 empty] | GFWG | VCAN, VANGO | VCCI | DFAT / GIZ |  |  |  | DFAT/GIZ start this activity in Q2 with the TA on Private Public Sector Engagement on CF. During the institutional review the assessment tool will be utilized and rolled out to other stakeholders (see 1.4.2).
|  |  | 1.5.2 |  |  | Undertake institutional review for GCF accreditation (National Implementing Entity status) and implement recommendations | [10 empty] | CFWG |  |  | PIFS, ISACC, DFAT/GIZ, GIZ Readiness, Climate Ready, UNDP. SPREP |  |  |  | PIFS and SPC, GIZ, Climate Ready partners are currently developing draft TOR "to conduct a review of the status of implementation of the Climate Public Expenditure and Institutional Review (CPEIR) for Vanuatu using the Pacific Climate Change Financing Assessment Framework (PCCFAF)" in Vanuatu for but not exclusively GCF accreditation. The institutional review is incorporated. This activity is suggested for May.
|  |  | 1.5.3 |  |  | Secure readiness funds to address gaps for direct accreditation and implement readiness activities | [10 empty] | CFWG |  |  | SPC ISACC, GIZ Readiness |  | 2 | 2
|  |  | 1.6 | Strengthen procurement capacity and/or policy at MFEM to bring into alignment with GCF/AF criteria | [12 empty] | MFEM | [6 empty] | Government audit issues need to be dealt with before accreditation. Does this need to be moved to Capacity Building/ Project Management respectively? Consider ease of reporting/roadmap logic
|  |  | 1.6.1 |  |  | Develop/review Procurement Guidelines with MFEM (alignment with 6.2) | [10 empty] | MFEM |  |  | Climate Ready, GIZ/DFAT |  |  |  | Recommended PFM related training (procurement, etc) be moved to capacity building - also acknowledge overlap with access to CF. GIZ/DFAT and CR requests procurement guidelines & training follow the completion of the Institutional Review and propose either action this activity towards the end of 2017 or early 2018. [CR] The accreditation requirements will question if training was carried out for the new procurement guidelines. It is pertinent that training follow the completion of the procurement guidelines - to comply with accreditation requirements.
|  |  | 1.6.2 |  |  | Deliver Procurement training for MFEM, MoCC, DSPPAC (alignment with 2. Capacity Building) | [10 empty] | MFEM |  |  | Climte Ready
|  |  | 1.6.3 |  |  | Develop a Central Tender Board website for procurement matters (alignment with 6.4) | [10 empty] | MFEM |  |  | GFG, PIFTAC, EU |  | 0 | 3
| MFEM and MoCC's PFM systems to improve implementation of curent projects (e.g. Direct Action) are strengthened, and aligned with PFM Roadmap (to be approved April 2017) |  | 1.7 | Strengthen MFEM, MoCC AND Project Managemnt Units' Public Finance and Project Management Systems | [15 empty] | DFAT / GIZ |  | 0 | 1 | Moved from Project Management as PFM relates to climate finance access, so should be under Objective 1
|  |  | 1.7.1 |  |  | Recruit an M&E and/or finance specialist (refer to CPEIR recommendations for capacity gaps) | [10 empty] | Aid Coordination Expert hosted in PMO/DSPPAC? |  |  | SPC ISACC |  |  |  | Recruit for three positions (GIZ Readiness, ISACC, Ready) to strengthen finance, climate and PMO at same time. MoCC / CFWG to send TOR to partners for approval of positions
|  |  | 1.7.2 |  |  | Support implementation of the MFEM PFEM Roadmap | [10 empty] | MFEM, CFWG |  |  | DFAT / GIZ among others
|  |  | 1.7.3 |  |  | Develop finance tracking tools in MFEM for on and off budget climate finance flows | [10 empty] | MFEM |  |  | DFAT / GIZ
|  |  | 1.7.4 |  |  | Utilise the EU-GIZ ACSE project on solar & biogas based rural electrification / Cyclone Pam recovery as a case study to identify areas in PFM that need improvement | [10 empty] | MoCC, MFEM |  |  | DFAT / GIZ
| Civil Society engagement in CF access and management processes is strengthened. Note overlap with other activities throughout Roadmap |  | 1.8 | Training delivered to CSO implementing partners to strengthen financial and project management capacity | [17 empty] | 2 | 3
|  |  | 1.8.1 |  |  | Finance management training provided to (and by) CSOs (MANGO training) | [10 empty] | Ministry of Internal Affairs | Oxfam, VANGO |  | USAID Climate Ready |  |  |  | MANGO- Management Training for NGO's offered by OXFAM. Need TORs to rollout MANGO at provincial/community level. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
|  |  | 1.8.2 |  |  | Training delivered to (and by) CSOs on M&E, governance and gender mainstreaming | [10 empty] | Ministry of Internal Affairs | CARE, Save the Children, Oxfam, VANGO |  | USAID Climate Ready |  |  |  | Climate Ready has a Gender expert, SPC/GIZ have developed a Climate Gender Toolkit, CARE in Vanuatu does Gender Mainstreaming. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
|  |  | 1.8.3 |  |  | Training delivered for (and by) CSOs on Risk Assessment and Safeguards Guidelines. | [10 empty] | Ministry of Internal Affairs | CARE, Save the Children, World Vision, Live and Learn |  | USAID Climate Ready |  |  |  | MIPU has already developed SSF and DEPC has legislation/regulations on Env Safeguards. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
| Private Sector engagement in CF access and management processes is strengthened. |  | 1.9 | Identify and implement public private partnerships that are aligned with the National Sustainable Development Plan ToR for Consultant: https://www.dropbox.com/s/6fef99s1bvbdhtx/VU_TOR%20DFATGIZ_PS_Engagement.pdf?dl=0 | [19 empty] | Consider creating role for PS/NGO "champions" (pollinators and plumbers) to ensure easy flow of information and proposals to and amongst Government Ministries
|  |  | 1.9.1 |  |  | Map private sectors' work as relevant to adaptation/mitigation impacts | [13 empty] | GIZ/DFAT |  |  |  | GIZ/DFAT circulated TOR for local consultancy incorporating most private sector related activities end of March 2017
|  |  | 1.9.2 |  |  | Create database mapping private sector actors against accredited institutions | [13 empty] | GIZ/DFAT
|  |  | 1.9.3 |  |  | Develop GCF concept notes for private-public partnership | [13 empty] | USAID Climate Ready, GIZ/DFAT, GIZ Readiness |  |  |  | [CR] CR can support development of Concept Notes in their advanced stages (close to submission) through any TA that may be required to complete the concept note (ref: Objective 2 of CR project: immediate and med-term priority)
|  |  | 1.9.4 |  |  | Undertake consultations with localprivate sector on their climate finance needs | [10 empty] | GFWG |  | VCCI | GIZ/DFAT
|  |  | 1.9.5 |  |  | Private Sector information on NAB Portal on CF rules/requirements/processes of GCF | [10 empty] | MoCC (NAB Secretariat), Dept of Land, Energy, Statistics, Agriculture | Village infrastructure | VCCI | GIZ Readiness
2. Capacity Building: National, provincial and community capacity strengthened to manage the impacts of climate change and disasters through new tools, systems, knowledge and approaches | Finance Management Capacity within PMO, AG Office, MFEM and MoCC is strengthened. |  | 2.1 | Undertake climate finance capacity assessment, specifically for MoCC, PMO and MFEM (aligned with sub-activity 1.4.1) | [12 empty] | CSUs of Ministries |  |  | PIFS, GIZ/DFAT |  | 3 | 5 | ensure that M&E is included in 2017 CF Assessment. GIZ/DFAT: This activity is incorporated into the CPEIR Review utilizing PCCFAF, lead by PIFS. See comment 1.4.2
| The capacity to coordinate finance and monitor climate change related projects is increasedby December 2020 |  | 2.2 | Conduct project management training (design, appraisal, action plans, implemetation, M&E and closure) (aligned with 1.5.2) | [12 empty] | MFEM, MoCC, provincial |  |  | UNCDF, USAID Readiness, SPC ISACC |  | 3 | 0
|  |  | 2.2.1 |  |  | Conduct national & provincial level project preparation training (for officers of Executing Entities) | [10 empty] | DLA, line agencies |  |  | USAID Climate Ready |  |  |  | [CR] CR can deliver on a CCA Project Preparation Training for Vanuatu at this time (Oct-Dec). The training requires participants to bring in serious/real draft proposals / concept notes to the trainings. (ref: Objective 2 of CR project: med-term priority)
|  |  | 2.3 | Recruit climate experts and coordinators for MoCC, MFEM and PMO | [12 empty] | MoCC, PMO, MFEM |  |  | Commonwealth Secretariat, SPC ISACC, GIZ Readiness, GFG |  | 0 | 0 | Currently Nikita Solzer (GIZ) @ NAB Secretariat, Margaret MacFarlane (GFG) @ NAB Secretariat
| Provincial officials' capacity to deliver climate financed projects is increased. |  | 2.4 | Develop a project management certification program (e.g. APCT, USP distance, VIT ) | [15 empty] | EU-Pac-TVET
|  |  | 2.5 | Conduct training and awareness for provincial officials on climate finance and allocation of resources | [13 empty] | LLEE, Oxfam (governance), CARE (gender, M&E) |  | GIZ / DFAT, SPC ISACC (joint design of modules) |  | 1 | 0 | GIZ has developed CF Training Modules which will be tailored to Pacific context.
|  |  | 2.6 | Train national and provincial officers to apply vulnerability, M&E and climate finance tracking tools and frameworks by December 2020 | [17 empty] | 0 | 0 | Activity can be picked up in 2018
3. Prioritisation: Ensuring allocation of resources is based on real vulnerabilities, gaps and needs | Project appraisal, prioritisation and allocation processes for CCDRR finance are strengthened. |  | 3.1 | Develop an integrated National Vulnerability Framework to guide climate finance investment and decision-making, and inform NSDP priorities | [12 empty] | NAB |  |  | GIZ Readiness, SPC ISACC |  | 2 | 5
|  |  | 3.1.1 |  |  | NAB/DSPPAC to utilise this Framework to allocate CF to projects assisting most vulnerable. | [10 empty] | NAB |  |  | GIZ Readiness, SPC ISACC |  | 2 | 0
|  |  | 3.1.2 |  |  | Pilot a whole-of-province CCDRR approach using an integrated National Vulnerabilty Framework | [15 empty] | 0 | 0 | Park until 2018
|  |  | 3.2 | Develop a CCDRR Policy Implementation Plan, Investment Strategy and M&E Framework | [12 empty] | NAB, DSPPAC, DoCC |  |  | UNEP (delayed), UNDP (NAP) |  | 2 | 3 | Park until 2018, see how Solomon's NAP comes out - is it more urgent to develop a NAP or CCDRR Implementation plan (or can they be the same thing?)
|  |  | 3.2.1 |  |  | Map out costs and activities to undertake an Implementation Plan for CCDRR Policy | [13 empty] | USAID Climate Ready |  |  |  | [CR] Climate Ready to follow up with UNEP
|  |  | 3.2.2 |  |  | Develop a Vanuatu Climate Finance Investment Strategy through a participatory process, and endorse by December 2017 | [9 empty] | MFEM, DSPPAC, NAB | MFEM, DSPPAC, NAB |  | VIPA, Financial Institutions | UNEP, NAP |  | 2 | 3 | GIZ/DFAT: Results of the CPEIR Review utilizing PIFS PCCFAF tool could be fed into this (see 1.4.2)
|  |  | 3.2.3 |  |  | Include specific, costed private sector needs and gaps in cliamte change investment strategy | [10 empty] | Trade Department | VANGO (needs funding and reform to be re-invented) | VCCI, Coops | DFAT/GIZ |  |  |  | Park until 2018. GIZ/DFAT: results of the policy recommendations and stakeholder consultations from the consultancy for public private sector engagement will feed into this (see 1.8). This should happen timely aligned to 3.2.2 the Investment Strategy.
|  |  | 3.2.4 |  |  | Develop a GCF Country Program (to inform whole-of-government Climate Finance Investment Strategy) 2017-2018 | [10 empty] | NDA, NAB Sec |  |  | GIZ Readiness
4. Awareness & Communications: Increased awareness on accessing & implementing climate (and disaster) finance at the national, provincial and community levels | Global awareness of Vanuatu's climate finance priorities and lessons is increased. |  | 4.1 | Participate at international and regional climate finance meetings | [15 empty] | SPC ISACC, GIZ/DFAT, Climate Ready |  | 1 | 0 | Note SPC ISACC and GIZ/DFAT July 2017 meeting in Nadi; Note potential for UNFCCC COP23 (regional?) side event on Climate Finance
|  |  | 4.1.1 |  |  | Identify relevant meetings and their agendas, and Vanuatu entry points
| Cross-sector communication about climate finance is improved. communication guidelines and web portal are established by 2018. |  | 4.2 | Develop and endorse a Vanuatu Climate Finance Communication Plan (with standardised message) | [12 empty] | MoCC |  |  | GIZ, SPC ISACC |  | 0 | 0 | ISACC support, to be carried out in 2018
|  |  | 4.2.1 |  |  | Disseminate targeted CF information and awareness materials for communities, govt, CSOs and PS through video
|  |  | 4.3 | Incorporate a Climate Finance Section on NAB Portal (include functionality within NAB portal for online discussion forums) | [12 empty] | MoCC (NAB) |  |  | GIZ Readiness |  | 1 | 1 | Complement physical meetings with virtual discussions (PS section on NAB Portal)
|  |  | 4.4 | Document and disseminate "lessons learned" on accessing and managing climate financed projects | [15 empty] | GIZ/DFAT, ISACC, Climate READY |  | 1 | 0
|  |  | 4.4.1 |  |  | Face-to-face consultations with CSOs, private sector, and GoV on climate change finance activities / aspirations | [13 empty] | GIZ / DFAT |  |  |  | Recommend moving to Coordination (making note to compliment face-to-face with virtual discussion space)
5. Coordination: Enhanced coordination with NGOs, CSOs and local communities to access & implement multi-sectoral, innovative approaches in addressing climate and disaster risks | Engagement between MFEM and MoCC is strengthened. - HL working group forum by end of 2017 - CoM paper on the delineation roles - Engage with PICs in South-South Coperation by end of 2017. |  | 5.1 | Clarify climate finance mandates among DSPPAC, NAB, MoCC, MoFT, MoCC and others | [12 empty] | NAB |  |  |  |  | 2 | 5
|  |  | 5.1.1 |  |  | Bilateral meetings among Director Generals | [17 empty] | Linked to CPEIR
|  |  | 5.1.2 |  |  | Council of Ministers Decision
|  |  | 5.1.3 |  |  | South-South cooperation on governance arrangements in other Pacific Island countries | [10 empty] | MoCC, MFEM, DSPPAC |  |  | DFAT / GIZ, ISACC, Climate Ready |  |  |  | Each supporting program can sponsor one south-south meeting each per year; good idea to join south-south discussions with sharing between countries on other programs (i.e. Samoa on CPEIR); whether an exchange program is viable? GIZ / DFAT to do costing.
| Coordination between the Government of Vanuatu, the private sector and civil society is strengthened. (Await review of CPEIR Action Plan) - 5 policies/regulations reviewed by end of 2020. |  | 5.2 | Develop and roll out single project management/ coordination platform (alignment with 5.1) | [12 empty] | PMO, MFEM, DLA (wait for review for CPEIR Action Plan) |  |  |  |  | 1 | 1
|  |  | 5.3 | Develop and implement National Coordination Guidelines for CCDRR finance | [12 empty] | PMO, MFEM, DSPPAC |  |  | DFAT / GIZ |  |  |  | See draft NAB Partnerships Policy and tools from Landua. GIZ/DFAT: after results from CPEIR review have been discussed. Probably starting end of 2017, early 2018
|  |  | 5.4 | Include CSO and private sector representatives on NAB Climate Finance Working Group (note power to invite other members to CFWG in ToR) | [12 empty] | NAB, CFWG | VCAN | VCCI Finance Institutions |  |  | 1 | 0
|  |  | 5.5 | MoCC to participate in existing private sector forums and groups | [12 empty] | MoCC | [6 empty] | GIZ/DFAT consultancy on private public sector engagement will make recommendations (see 1.8)
| Decision-making processes affecting climate finance are harmonised. Twenty (20) decision making committees start tracking CF by 2020. |  | 5.6 | Incorporate climate finance into national and provincial decision making platforms (TACs, industry working groups, provincial councils etc) | [12 empty] | DSPPAC, NAB, MFEM |  |  | MIA |  | 4 | 5 | Focus on Financial Service Bureaus (links to MFEM)
| Processes, policies and legislation affecting climate finance are reviewed and harmonised. or 5 policies/regulations by end of 2020. |  | 5.7 | Review key Policy, Legislation & Regulations of relevance to Climate Finance | [12 empty] | MFEM, CFWG, AGO, SLO, DoCC |  |  | PFTAC, GFG (DFAT), VCAP |  | 3 | 3
|  |  | 5.7.1 |  |  | Review the Decentralisation Act to include climate finance considerations | [10 empty] | DLA |  |  | VCAP, UNDP |  | 0 | 0
|  |  | 5.7.2 |  |  | Review the Public Finance Management Act | [10 empty] | MFEM |  |  | DFAT / GIZ, Climate Ready |  | 0 | 0 | Included in PFM Roadmap
6. Project Management: Project Management Capacity at the national and provincial levels are strengthened to address multi-sector & sectoral responses to climate change and disaster risks by end of 2020. | Management practices across Government dealing with climate finance are improved. Five (5) guidelines to be developed by end of 2020. |  | 6.1 | Develop resources to support climate project management (including M&E) at all levels
|  |  | 6.1.1 |  |  | Develop and Strengthen M&E Guidelines | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | IRCCNH, ISACC |  | 2 | 2
|  |  | 6.1.2 |  |  | Develop / strengthen Project Preparation and Appraisal Guidelines (see IRCCNH M&E pilot) | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | GIZ Readiness, ISACC |  | 1 | 2 | IRCCNH have guidelines
|  |  | 6.1.3 |  |  | Develop Risk Assessment and Safeguards Guidelines for use by govt sectors, PS and CSOs | [10 empty] | DSPPAC, NAB, MoCC, MFEM | CARE, Save the Children, World Vision, Live and Learn |  | GIZ Readiness, UNDP PRP |  | 0 | 2 | PRRP has developed a tool for screening Risk at Provincal Level
|  |  | 6.1.4 |  |  | Develop, strengthen and operationalise Project Closure Guidelines | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | ISACC |  | 0 | 1
|  |  | 6.1.5 |  |  | Develop a CCDRR M&E Framework | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | IRCCNH, ISACC |  | 2 | 5 | Build on IRCCNH M&E Framework; highurgency, as no one is tracking climate projects yet. Includes broader thinking relating tooutcomes (not just activity, what are the results?) Must be linked to NSDP and CCDRR Policy
|  |  | 6.1.6 |  |  | Develop and finalise CC/DRR Project Management Manual | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | ISACC (if they have funds) |  | 0 | 2 | An operations manual (e.g. ISACC developed one for Palau) - link with GIZ project under Readiness. This Manual should include "lessons learned" on cliate finance. SPREP already has Guidelines, but needs to be updated and have examples included
|  |  | 6.1.7 |  |  | Develop project management tools and guidelines to support national and provincial governments | [10 empty] | DSPPAC, NAB, MoCC, MFEM |  | World Vision | ISACC, Climate Ready |  | 1 | 1 | Linked to Capacity Building (2).
|  |  | 6.2 | The PMUs and NAB Sec's capacity for climate finance and project management is strengthened (fully staffed and skills enhanced with CF & project management by end of 2020). | [19 empty] | Linked to Capacity Building (2) training beneficiaries to include CFWG and PMU
| MFEM and MoCC's PFM systems to improve implementation of curent projects (e.g. Direct Action) are strengthened. CTB website established by end of 2018, 50% of off budget CF flows are tracked by MOF by 2020. |  | 6.3 | Strengthen MFEM and MoCC Public Finance Management System by implementing MFEM's PFM Roadmap | [15 empty] | DFAT / GIZ |  | 0 | 1 | Reference PFM Roadmap and include sub-activities relating to climate finance. GIZ/DFAT plans to starat this support as early as possible, however, some need to wait for the CPEIR review to be completed.
|  |  | 6.3.1 |  |  | Develop finance tracking tools for on and off budget flows, including specific section for CF | [13 empty] | DFAT / GIZ
|  |  | 6.3.2 |  |  | Strengthen MFEM and MoCC's PFM systems to improve implementation of current projects e.g. Direct Access | [10 empty] | MFEM |  |  | DFAT / GIZ, GFG, PFTAC, EU |  | 1 | 0
|  |  | 6.3.3 |  |  | Develop a Central Tender Board website for procurement matters | [10 empty] | MFEM |  |  | DFAT / GIZ, GFG, PFTAC, EU |  | 0 | 1
Note on H8: Vuki Buadromo: Is this action plan the same as the Climate Finance Roadmap?? If it is, suggest we amend the text so that its consistent & avoids confusion
Note on V17: Vuki Buadromo: Suggest we remove PIFS as ISACC covers SPC, PIFS & SPREP

## 2017 work plan
Vanuatu Draft Climate Finance Roadmap 2016-2020 Based on the recommendations of the 2014 CPEIR, the 2016 Climate Finance Forum, the CCDRR Policy, the PFEM Roadmap, and 2017 Consultations |  |  |  |  | Roadmap Focal Point: |  | Wycliff Bakeo |  |  | NAB CFWG & Prime Minister's Offcie (DSPPAC)
[5 empty] | Version Control 18.04.17 |  |  |  |  | wbakeo@vanuatu.gov.vu
Comments DFAT/GIZ HS from 31.03.17, SPC/ISACC - 18.4.17
Climate Finance Policy Objectives | Targets | Indicators | Ref number | Activities | Sub-Activities | Status of Activities | Timelines |  |  |  |  | Partnerships |  |  |  | Notes
[7 empty] | Q4, 2016 | Q1, 2017 | Q2, 2017 | Q3, 2017 | Q4, 2017 | Govt | NGOs & CSOs | Private Sector | Development Partners
1. Access to Climate Change Finance: Vanuatu has access to direct and indirect new sources of climate and disaster finances to adapt to and mitigate the impacts of climate change. | The Government of Vanuatu's access to climate finance is increased - adaptation share of climate finance investment is at least 50%. |  | 1.1 | NAB establishes the Climate Finance Working Group to develop, monitor and report against the National Climate Finance Roadmap |  | Completed and on-tracking | [5 empty] | CFWG, PMO, NAB | VCAN | VCCI | GIZ, UNDP, ISACC
|  |  | 1.1.1 |  | NAB develops and endorses CFWG Terms of Reference and multi-year action plan | [6 empty] | NAB Sec |  |  | GIZ
|  |  | 1.2 | Develop and endorse a National Climate Finance Roadmap |  | Completed (National CF Roadmap to be presented /endorsed by the NAB) | [5 empty] | CFWG |  |  | SPC/GIZ, DFAT/GIZ, GIZ Readiness, ISAAC, UNDP | Govt. needs to nominate focal point for Climate Finance Roadmap; Development Partners can support the focal point when and if requested. Development partners fit specific developments into this Roadmap through the focal point.
|  |  | 1.2.1 |  | Identify key national priorities through a Climate Finance Forum | Completed | [5 empty] | PMO, DSPPAC |  |  | DFAT / GIZ, ISACC
|  |  | 1.3 | Work towards implementing the CCDRR policy to have equal share of adaptation and mitigation CF projects |  | On track
|  |  | 1.3.1 |  | Design, approve and implement bankable, multi-sector projects and program proposals | On track | [6 empty] | Save the Children (proposal in pipeline) |  | Climate Ready, DFAT / GIZ, ISACC, GIZ Readiness, ADB (proposal in pipeline) | See extensive sub-activities under private sector engagement on this activity. Note that NAB keeps a rolling database of GCF concept notes. Worth having a public facing, collaborative copy of this database? See Activity 5.2. CARE & Save the Children have expressed interest in collaborating on this activity. GIZ/DFAT starts this activity rather in the Q4 of 2017, unless opportunities arise earlier. CR will also consider this activity in Q4 of 2017
| - At least one national entity is accredited as an NIE to the GCF/AF by 2020 - At least 80% of CPEIR recommendations are implemented by December 2017. |  | 1.4 | Seek GCF/AF NIE Accreditation |  | On track | [5 empty] | MoCC
|  |  | 1.4.1 |  | Roll out self assessment tool to selected NGOs, PS and government entities | On track | [5 empty] | GFWG | VCAN, VANGO | VCCI | DFAT / GIZ | DFAT/GIZ start this activity in Q2 with the TA on Private Public Sector Engagement on CF. During the institutional review the assessment tool will be utilized and rolled out to other stakeholders (see 1.4.2).
|  |  | 1.4.2 |  | Undertake institutional review for GCF accreditation (National Implementing Entity status) and implement recommendations | On track | [5 empty] | CFWG |  |  | PIFS, ISACC, DFAT/GIZ, GIZ Readiness, Climate Ready, UNDP. SPREP | PIFS and SPC, GIZ, Climate Ready partners are currently developing draft TOR "to conduct a review of the status of implementation of the Climate Public Expenditure and Institutional Review (CPEIR) for Vanuatu using the Pacific Climate Change Financing Assessment Framework (PCCFAF)" in Vanuatu for but not exclusively GCF accreditation. The institutional review is incorporated. This activity is suggested for May.
|  |  | 1.4.3 |  | Secure readiness funds to address gaps for direct accreditation and implement readiness activities | On track | [5 empty] | CFWG |  |  | SPC ISACC, GIZ Readiness
|  |  | 1.5 | Strengthen procurement capacity and/or policy at MFEM to bring into alignment with GCF/AF criteria | [7 empty] | MFEM |  |  |  | Government audit issues need to be dealt with before accreditation. Does this need to be moved to Capacity Building/ Project Management respectively? Consider ease of reporting/roadmap logic
|  |  | 1.5.1 |  | Develop/review Procurement Guidelines with MFEM (alignment with 6.2) | [6 empty] | MFEM |  |  | Climate Ready, GIZ/DFAT | Recommended PFM related training (procurement, etc) be moved to capacity building - also acknowledge overlap with access to CF. GIZ/DFAT and CR requests procurement guidelines & training follow the completion of the Institutional Review and propose either action this activity towards the end of 2017 or early 2018. [CR] The accreditation requirements will question if training was carried out for the new procurement guidelines. It is pertinent that training follow the completion of the procurement guidelines - to comply with accreditation requirements.
|  |  | 1.5.2 |  | Deliver Procurement training for MFEM, MoCC, DSPPAC (alignment with 2. Capacity Building) | [6 empty] | MFEM |  |  | Climte Ready
|  |  | 1.5.3 |  | Develop a Central Tender Board website for procurement matters (alignment with 6.4) | [6 empty] | MFEM |  |  | GFG, PIFTAC, EU
| MFEM and MoCC's PFM systems to improve implementation of curent projects (e.g. Direct Action) are strengthened, and aligned with PFM Roadmap (to be approved April 2017) |  | 1.6 | Strengthen MFEM, MoCC AND Project Managemnt Units' Public Finance and Project Management Systems | [10 empty] | DFAT / GIZ | Moved from Project Management as PFM relates to climate finance access, so should be under Objective 1
|  |  | 1.6.1 |  | Recruit an M&E and/or finance specialist (refer to CPEIR recommendations for capacity gaps) | On track - ISACC to support M&E specialist to be based with the PMO/DSPPAC. | [5 empty] | Aid Coordination Expert hosted in PMO/DSPPAC? |  |  | SPC ISACC | Recruit for three positions (GIZ Readiness, ISACC, Ready) to strengthen finance, climate and PMO at same time. MoCC / CFWG to send TOR to partners for approval of positions
|  |  | 1.6.2 |  | Support implementation of the MFEM PFEM Roadmap | On track | [5 empty] | MFEM, CFWG |  |  | DFAT / GIZ among others
|  |  | 1.6.3 |  | Develop finance tracking tools in MFEM for on and off budget climate finance flows | On track | [5 empty] | MFEM |  |  | DFAT / GIZ
|  |  | 1.6.4 |  | Utilise the EU-GIZ ACSE project on solar & biogas based rural electrification / Cyclone Pam recovery as a case study to identify areas in PFM that need improvement | On track | [5 empty] | MoCC, MFEM |  |  | DFAT / GIZ
| Civil Society engagement in CF access and management processes is strengthened. Note overlap with other activities throughout Roadmap |  | 1.7 | Training delivered to CSO implementing partners to strengthen financial and project management capacity
|  |  | 1.7.1 |  | Finance management training provided to (and by) CSOs (MANGO training) | On track | [5 empty] | Ministry of Internal Affairs | Oxfam, VANGO |  | USAID Climate Ready | MANGO- Management Training for NGO's offered by OXFAM. Need TORs to rollout MANGO at provincial/community level. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
|  |  | 1.7.2 |  | Training delivered to (and by) CSOs on M&E, governance and gender mainstreaming | On track | [5 empty] | Ministry of Internal Affairs | CARE, Save the Children, Oxfam, VANGO |  | USAID Climate Ready | Climate Ready has a Gender expert, SPC/GIZ have developed a Climate Gender Toolkit, CARE in Vanuatu does Gender Mainstreaming. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
|  |  | 1.7.3 |  | Training delivered for (and by) CSOs on Risk Assessment and Safeguards Guidelines. | On track | [5 empty] | Ministry of Internal Affairs | CARE, Save the Children, World Vision, Live and Learn |  | USAID Climate Ready | MIPU has already developed SSF and DEPC has legislation/regulations on Env Safeguards. [CR] USAID CR may only support these training needs as part of 1 - a pipeline proposal / program; or 2 - an ongoing CCA project /program already identified as an activity/need of that project / program (ref: Objective 3 of the CR Project: med-term priority)
| Private Sector engagement in CF access and management processes is strengthened. |  | 1.8 | Identify and implement public private partnerships that are aligned with the National Sustainable Development Plan |  | On track | [9 empty] | Consider creating role for PS/NGO "champions" (pollinators and plumbers) to ensure easy flow of information and proposals to and amongst Government Ministries
|  |  | 1.8.1 |  | Map private sectors' work as relevant to adaptation/mitigation impacts | On track | [8 empty] | GIZ/DFAT | GIZ/DFAT circulated TOR for local consultancy incorporating most private sector related activities end of March 2017
|  |  | 1.8.2 |  | Create database mapping private sector actors against accredited institutions | On track | [8 empty] | GIZ/DFAT
|  |  | 1.8.3 |  | Develop GCF concept notes for private-public partnership | On track | [8 empty] | USAID Climate Ready, GIZ/DFAT, GIZ Readiness | [CR] CR can support development of Concept Notes in their advanced stages (close to submission) through any TA that may be required to complete the concept note (ref: Objective 2 of CR project: immediate and med-term priority)
|  |  | 1.8.4 |  | Undertake consultations with localprivate sector on their climate finance needs | On track | [5 empty] | GFWG |  | VCCI | GIZ/DFAT
|  |  | 1.8.5 |  | Private Sector information on NAB Portal on CF rules/requirements/processes of GCF | On track | [5 empty] | MoCC (NAB Secretariat), Dept of Land, Energy, Statistics, Agriculture | Village infrastructure | VCCI | GIZ Readiness
2. Capacity Building: National, provincial and community capacity strengthened to manage the impacts of climate change and disasters through new tools, systems, knowledge and approaches | Finance Management Capacity within PMO, AG Office, MFEM and MoCC is strengthened. |  | 2.1 | Undertake climate finance capacity assessment, specifically for MoCC, PMO and MFEM (aligned with sub-activity 1.4.1) |  | On track | [5 empty] | CSUs of Ministries |  |  | PIFS, GIZ/DFAT | ensure that M&E is included in 2017 CF Assessment. GIZ/DFAT: This activity is incorporated into the CPEIR Review utilizing PCCFAF, lead by PIFS. See comment 1.4.2
| The capacity to coordinate finance and monitor climate change related projects is increasedby December 2020 |  | 2.2 | Conduct project management training (design, appraisal, action plans, implemetation, M&E and closure) (aligned with 1.5.2) |  | On track | [5 empty] | MFEM, MoCC, provincial |  |  | UNCDF, USAID Readiness, SPC ISACC
|  |  | 2.2.1 |  | Conduct national & provincial level project preparation training (for officers of Executing Entities) | On track | [5 empty] | DLA, line agencies |  |  | USAID Climate Ready | [CR] CR can deliver on a CCA Project Preparation Training for Vanuatu at this time (Oct-Dec). The training requires participants to bring in serious/real draft proposals / concept notes to the trainings. (ref: Objective 2 of CR project: med-term priority)
|  |  | 2.3 | Recruit climate experts and coordinators for MoCC, MFEM and PMO |  | On track | [5 empty] | MoCC, PMO, MFEM |  |  | Commonwealth Secretariat, SPC ISACC, GIZ Readiness, GFG | Currently Nikita Solzer (GIZ) @ NAB Secretariat, Margaret MacFarlane (GFG) @ NAB Secretariat
| Provincial officials' capacity to deliver climate financed projects is increased. |  | 2.4 | Develop a project management certification program (e.g. APCT, USP distance, VIT ) |  | On track | [8 empty] | EU-Pac-TVET
|  |  | 2.5 | Conduct training and awareness for provincial officials on climate finance and allocation of resources |  | On track | [6 empty] | LLEE, Oxfam (governance), CARE (gender, M&E) |  | GIZ / DFAT, SPC ISACC (joint design of modules) | GIZ has developed CF Training Modules which will be tailored to Pacific context.
|  |  | 2.6 | Train national and provincial officers to apply vulnerability, M&E and climate finance tracking tools and frameworks by December 2020 |  | On track | [9 empty] | Activity can be picked up in 2018
3. Prioritisation: Ensuring allocation of resources is based on real vulnerabilities, gaps and needs | Project appraisal, prioritisation and allocation processes for CCDRR finance are strengthened. |  | 3.1 | Develop an integrated National Vulnerability Framework to guide climate finance investment and decision-making, and inform NSDP priorities |  | On track | [5 empty] | NAB |  |  | GIZ Readiness, SPC ISACC
|  |  | 3.1.1 |  | NAB/DSPPAC to utilise this Framework to allocate CF to projects assisting most vulnerable. | On track | [5 empty] | NAB |  |  | GIZ Readiness, SPC ISACC
|  |  | 3.1.2 |  | Pilot a whole-of-province CCDRR approach using an integrated National Vulnerabilty Framework | On track | [9 empty] | Park until 2018
|  |  | 3.2 | Develop a CCDRR Policy Implementation Plan, Investment Strategy and M&E Framework |  | On track | [5 empty] | NAB, DSPPAC, DoCC |  |  | UNEP (delayed), UNDP (NAP) | Park until 2018, see how Solomon's NAP comes out - is it more urgent to develop a NAP or CCDRR Implementation plan (or can they be the same thing?)
|  |  | 3.2.1 |  | Map out costs and activities to undertake an Implementation Plan for CCDRR Policy | On track | [8 empty] | USAID Climate Ready | [CR] Climate Ready to follow up with UNEP
|  |  | 3.2.2 |  | Develop a Vanuatu Climate Finance Investment Strategy through a participatory process, and endorse by December 2017 | On track | [5 empty] | MFEM, DSPPAC, NAB |  | VIPA, Financial Institutions | UNEP, NAP | GIZ/DFAT: Results of the CPEIR Review utilizing PIFS PCCFAF tool could be fed into this (see 1.4.2)
|  |  | 3.2.3 |  | Include specific, costed private sector needs and gaps in cliamte change investment strategy | On track | [5 empty] | Trade Department | VANGO (needs funding and reform to be re-invented) | VCCI, Coops | DFAT/GIZ | Park until 2018. GIZ/DFAT: results of the policy recommendations and stakeholder consultations from the consultancy for public private sector engagement will feed into this (see 1.8). This should happen timely aligned to 3.2.2 the Investment Strategy.
|  |  | 3.2.4 |  | Develop a GCF Country Program (to inform whole-of-government Climate Finance Investment Strategy) 2017-2018 | On track | [5 empty] | NDA, NAB Sec |  |  | GIZ Readiness
4. Awareness & Communications: Increased awareness on accessing & implementing climate (and disaster) finance at the national, provincial and community levels | Global awareness of Vanuatu's climate finance priorities and lessons is increased. |  | 4.1 | Participate at international and regional climate finance meetings |  | On track | [8 empty] | SPC ISACC, GIZ/DFAT, Climate Ready | Note SPC ISACC and GIZ/DFAT July 2017 meeting in Nadi; Note potential for UNFCCC COP23 (regional?) side event on Climate Finance
|  |  | 4.1.1 |  | Identify relevant meetings and their agendas, and Vanuatu entry points | On track
| Cross-sector communication about climate finance is improved. communication guidelines and web portal are established by 2018. |  | 4.2 | Develop and endorse a Vanuatu Climate Finance Communication Plan (with standardised message) |  | Move to 2018 | [5 empty] | MoCC |  |  | GIZ, ISACC | ISACC support, to be carried out in 2018
|  |  | 4.2.1 |  | Disseminate targeted CF information and awareness materials for communities, govt, CSOs and PS through video | On track
|  |  | 4.3 | Incorporate a Climate Finance Section on NAB Portal (include functionality within NAB portal for online discussion forums) |  | On track | [5 empty] | MoCC (NAB) |  |  | GIZ Readiness | Complement physical meetings with virtual discussions (PS section on NAB Portal)
|  |  | 4.4 | Document and disseminate "lessons learned" on accessing and managing climate financed projects |  | On track | [8 empty] | ISACC, DFAT/GIZ
|  |  | 4.4.1 |  | Face-to-face consultations with CSOs, private sector, and GoV on climate change finance activities / aspirations | On track | [8 empty] | GIZ / DFAT | Recommend moving to Coordination (making note to compliment face-to-face with virtual discussion space)
5. Coordination: Enhanced coordination with NGOs, CSOs and local communities to access & implement multi-sectoral, innovative approaches in addressing climate and disaster risks | Engagement between MFEM and MoCC is strengthened. - HL working group forum by end of 2017 - CoM paper on the delineation roles - Engage with PICs in South-South Coperation by end of 2017. |  | 5.1 | Clarify climate finance mandates among DSPPAC, NAB, MoCC, MoFT, MoCC and others |  | On track | [5 empty] | NAB
|  |  | 5.1.1 |  | Bilateral meetings among Director Generals | On track | [9 empty] | Linked to CPEIR
|  |  | 5.1.2 |  | Council of Ministers Decision | On track
|  |  | 5.1.3 |  | South-South cooperation on governance arrangements in other Pacific Island countries | On track | [5 empty] | MoCC, MFEM, DSPPAC |  |  | DFAT / GIZ, ISACC, Climate Ready | Each supporting program can sponsor one south-south meeting each per year; good idea to join south-south discussions with sharing between countries on other programs (i.e. Samoa on CPEIR); whether an exchange program is viable? GIZ / DFAT to do costing.
| Coordination between the Government of Vanuatu, the private sector and civil society is strengthened. (Await review of CPEIR Action Plan) - 5 policies/regulations reviewed by end of 2020. |  | 5.2 | Develop and roll out single project management/ coordination platform (alignment with 5.1) |  | On track | [5 empty] | PMO, MFEM, DLA (wait for review for CPEIR Action Plan)
|  |  | 5.3 | Develop and implement National Coordination Guidelines for CCDRR finance |  | On track or move to 2018??? | [5 empty] | PMO, MFEM, DSPPAC |  |  | DFAT / GIZ | See draft NAB Partnerships Policy and tools from Landua. GIZ/DFAT: after results from CPEIR review have been discussed. Probably starting end of 2017, early 2018
|  |  | 5.4 | Include CSO and private sector representatives on NAB Climate Finance Working Group (note power to invite other members to CFWG in ToR) |  | On track | [5 empty] | NAB, CFWG | VCAN | VCCI Finance Institutions
|  |  | 5.5 | MoCC to participate in existing private sector forums and groups |  | On track | [5 empty] | MoCC |  |  |  | GIZ/DFAT consultancy on private public sector engagement will make recommendations (see 1.8)
| Decision-making processes affecting climate finance are harmonised. Twenty (20) decision making committees start tracking CF by 2020. |  | 5.6 | Incorporate climate finance into national and provincial decision making platforms (TACs, industry working groups, provincial councils etc) |  | On track | [5 empty] | DSPPAC, NAB, MFEM |  |  | MIA | Focus on Financial Service Bureaus (links to MFEM)
| Processes, policies and legislation affecting climate finance are reviewed and harmonised. or 5 policies/regulations by end of 2020. |  | 5.7 | Review key Policy, Legislation & Regulations of relevance to Climate Finance |  | On track | [5 empty] | MFEM, CFWG, AGO, SLO, DoCC |  |  | PFTAC, GFG (DFAT), VCAP
|  |  | 5.7.1 |  | Review the Decentralisation Act to include climate finance considerations | On track | [5 empty] | DLA |  |  | VCAP, UNDP
|  |  | 5.7.2 |  | Review the Public Finance Management Act | On track | [5 empty] | MFEM |  |  | DFAT / GIZ, Climate Ready | Included in PFM Roadmap
6. Project Management: Project Management Capacity at the national and provincial levels are strengthened to address multi-sector & sectoral responses to climate change and disaster risks by end of 2020. | Management practices across Government dealing with climate finance are improved. Five (5) guidelines to be developed by end of 2020. |  | 6.1 | Develop resources to support climate project management (including M&E) at all levels |  | On track
|  |  | 6.1.1 |  | Develop and Strengthen M&E Guidelines | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | IRCCNH, ISACC
|  |  | 6.1.2 |  | Develop / strengthen Project Preparation and Appraisal Guidelines (see IRCCNH M&E pilot) | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | GIZ Readiness, ISACC | IRCCNH have guidelines
|  |  | 6.1.3 |  | Develop Risk Assessment and Safeguards Guidelines for use by govt sectors, PS and CSOs | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM | CARE, Save the Children, World Vision, Live and Learn |  | GIZ Readiness, UNDP PRP | PRRP has developed a tool for screening Risk at Provincal Level
|  |  | 6.1.4 |  | Develop, strengthen and operationalise Project Closure Guidelines | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | ISACC
|  |  | 6.1.5 |  | Develop a CCDRR M&E Framework | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | IRCCNH, ISACC | Build on IRCCNH M&E Framework; highurgency, as no one is tracking climate projects yet. Includes broader thinking relating tooutcomes (not just activity, what are the results?) Must be linked to NSDP and CCDRR Policy
|  |  | 6.1.6 |  | Develop and finalise CC/DRR Project Management Manual | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  |  | ISACC (if they have funds) | An operations manual (e.g. ISACC developed one for Palau) - link with GIZ project under Readiness. This Manual should include "lessons learned" on cliate finance. SPREP already has Guidelines, but needs to be updated and have examples included
|  |  | 6.1.7 |  | Develop project management tools and guidelines to support national and provincial governments | On track | [5 empty] | DSPPAC, NAB, MoCC, MFEM |  | World Vision | ISACC, Climate Ready | Linked to Capacity Building (2).
|  |  | 6.2 | The PMUs and NAB Sec's capacity for climate finance and project management is strengthened (fully staffed and skills enhanced with CF & project management by end of 2020). |  | On track | [9 empty] | Linked to Capacity Building (2) training beneficiaries to include CFWG and PMU
| MFEM and MoCC's PFM systems to improve implementation of curent projects (e.g. Direct Action) are strengthened. CTB website established by end of 2018, 50% of off budget CF flows are tracked by MOF by 2020. |  | 6.3 | Strengthen MFEM and MoCC Public Finance Management System by implementing MFEM's PFM Roadmap |  | On track | [8 empty] | DFAT / GIZ | Reference PFM Roadmap and include sub-activities relating to climate finance. GIZ/DFAT plans to starat this support as early as possible, however, some need to wait for the CPEIR review to be completed.
|  |  | 6.3.1 |  | Develop finance tracking tools for on and off budget flows, including specific section for CF | On track - move to 2018 | [5 empty] | MFEM, MoCC, DSPPAC |  |  | DFAT / GIZ, ISACC
|  |  | 6.3.2 |  | Strengthen MFEM and MoCC's PFM systems to improve implementation of current projects e.g. Direct Access | On track | [5 empty] | MFEM |  |  | DFAT / GIZ, GFG, PFTAC, EU
|  |  | 6.3.3 |  | Develop a Central Tender Board website for procurement matters | On track | [5 empty] | MFEM |  |  | DFAT / GIZ, GFG, PFTAC, EU
Note on G9: Vuki Buadromo: Is this action plan the same as the Climate Finance Roadmap?? If it is, suggest we amend the text so that its consistent & avoids confusion
Note on Q16: Vuki Buadromo: Suggest we remove PIFS as ISACC covers SPC, PIFS & SPREP
Note on H23: Vuki Buadromo TOR for position to be shared with DSPPAC and MoCC for comment/approval. LOA to be signed prior to position being recruited